## Sheet1
Sprint 1
US ID | Task ID | Task Description | Start | End | Team Member | Activity | Status | Est (hrs)
US001 | T1 | Gather enterprise-style support email datasets | 2025-11-27 | 2025-11-28 | Data Engineering Team | Others | Done | 4
US001 | T2 | Consolidate datasets into unified corpus | 2025-11-29 | 2025-11-30 | Data Engineering Team | Build | Done | 3
US002 | T3 | Remove signatures, greetings & quoted replies | 2025-12-01 | 2025-12-02 | Data Engineering Team | Coding | Done | 6
US002 | T4 | Normalize text & punctuation cleanup | 2025-12-03 | 2025-12-04 | Data Engineering Team | Coding | Done | 5
US002 | T5 | Stopword removal & token refinement | 2025-12-05 | 2025-12-06 | Data Engineering Team | Coding | Done | 6
US003 | T6 | Design category label taxonomy | 2025-12-07 | 2025-12-08 | Data Team | Design | Done | 4
US003 | T7 | Design urgency level taxonomy | 2025-12-09 | 2025-12-09 | Data Team | Design | Done | 3
US003 | T8 | Annotate representative sample dataset | 2025-12-10 | 2025-12-11 | Data Team | Others | Done | 6
Sprint 2
US004 | T9 | Split dataset into train / validation / test sets | 2025-12-12 | 2025-12-13 | Data Engineering Team | Build | Done | 3
US006 | T10 | Implement Logistic Regression training script | 2025-12-14 | 2025-12-15 | ML Team | Coding | Done | 6
US006 | T11 | Implement Naive Bayes baseline classifier | 2025-12-16 | 2025-12-17 | ML Team | Coding | Done | 6
US007 | T12 | Fine-tune DistilBERT for email classification | 2025-12-18 | 2025-12-20 | ML Team | Coding | Done | 10
US008 | T13 | Evaluate models using Precision / Recall / F1 | 2025-12-21 | 2025-12-22 | QA Team | Unit Test | Done | 6
US009 | T14 | Implement multi-class classification pipeline | 2025-12-23 | 2025-12-24 | ML Team | Build | Done | 8
US010 | T15 | Develop internal inference API for classification engine | 2025-12-24 | 2025-12-25 | Backend Team | Coding | Done | 6
Sprint 3
US011 | T16 | Train urgency classifier (High / Medium / Low) | 2025-12-29 | 2025-12-30 | ML Team | Coding | Done | 8
US011 | T17 | Validate urgency model outputs | 2025-12-31 | 2026-01-01 | QA Team | Unit Test | Done | 6
US012 | T18 | Implement keyword-based urgency rules | 2026-01-02 | 2026-01-03 | ML Team | Coding | Done | 5
US012 | T19 | Combine ML urgency score + rule weighting | 2026-01-04 | 2026-01-05 | ML Team | Build | Done | 6
US013 | T20 | Validate urgency scoring with confusion matrix | 2026-01-06 | 2026-01-07 | QA Team | Integration Test | Done | 4
US014 | T21 | Integrate category + urgency into unified response schema | 2026-01-07 | 2026-01-08 | Backend Team | Build | Done | 6
Sprint4
US015 | T22 | Design dashboard layout & information hierarchy | 2026-01-09 | 2026-01-10 | Frontend Team | Design | In Progress | 6
US015 | T23 | Build real-time email view with category & urgency indicators | 2026-01-11 | 2026-01-13 | Frontend Team | Coding | In Progress | 10
US016 | T24 | Implement dashboard filters (category, urgency, date) | 2026-01-14 | 2026-01-15 | Frontend Team | Coding | Not Started | 6
US016 | T25 | Implement analytics (volume trends & complaint types) | 2026-01-16 | 2026-01-18 | Frontend Team | Build | Not Started | 6
US017 | T26 | Cloud deployment & API gateway setup | 2026-01-21 | 2026-01-22 | DevOps Team | Build | Not Started | 8
US018 | T27 | End-to-end validation with simulated email stream | 2026-01-23 | 2026-01-25 | QA Team | System Test | Not Started | 8
US018 | T28 | Final regression testing & stabilization | 2026-01-26 | 2026-01-27 | QA Team | Regression Test | Not Started | 6

## Sheet2
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
| P0 |  | Not started
| P1 |  | In progress
| P2 |  | Blocked
| P3 |  | Completed