## Sheet1
Sl No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect
1 | 2025-11-27 | Email preprocessing not removing signatures in some customer emails | Sprint 1 | Data Engineering Team | Functional
2 | 2025-11-29 | Tokenization producing incorrect tokens for special characters | Sprint 1 | Data Engineering Team | Logic
3 | 2025-12-01 | Labeled dataset contains inconsistent category values | Sprint 1 | Data Team | Data Issue
4 | 2025-12-03 | Model training script failing for missing email body | Sprint 1 | ML Team | Model Training
5 | 2025-12-05 | Stopword removal affecting important keywords | Sprint 1 | Data Engineering Team | Algorithmic
6 | 2025-12-07 | Baseline classifier accuracy lower than expected | Sprint 1 | ML Team | Algorithmic
7 | 2025-12-09 | Dataset split causing class imbalance | Sprint 1 | Data Team | Data Issue
8 | 2025-12-10 | Preprocessed dataset not saved correctly | Sprint 1 | Data Engineering Team | Functional
9 | 2025-12-12 | Logistic Regression model producing inconsistent predictions | Sprint 2 | ML Team | Algorithmic
10 | 2025-12-14 | Naive Bayes model misclassifying short emails | Sprint 2 | ML Team | Model Training
11 | 2025-12-16 | DistilBERT fine-tuning taking excessive training time | Sprint 2 | ML Team | Performance
12 | 2025-12-18 | Precision and recall calculation mismatch | Sprint 2 | QA Team | Logic
13 | 2025-12-21 | Multi-class categorization missing some labels | Sprint 2 | ML Team | Functional
14 | 2025-12-23 | API returning incomplete classification response | Sprint 2 | Backend Team | Integration
15 | 2025-12-24 | Internal classification API failing for large requests | Sprint 2 | Backend Team | Performance
16 | 2025-12-29 | Urgency prediction model misclassifying borderline emails | Sprint 3 | ML Team | Algorithmic
17 | 2025-12-31 | Rule-based urgency keywords not triggering correctly | Sprint 3 | ML Team | Logic
18 | 2026-01-02 | Combined urgency score not calculated correctly | Sprint 3 | Backend Team | Integration
19 | 2026-01-04 | Confusion matrix values not matching expected results | Sprint 3 | QA Team | Functional
20 | 2026-01-06 | Backend service failing to merge category and urgency output | Sprint 3 | Backend Team | Integration
21 | 2026-01-07 | API latency increases during bulk email processing | Sprint 3 | Backend Team | Performance